## Sheet1
Product Backlog
# | Task | Description | Priority (1-10) | Resources Required (Hours) | Start Date | Due Date | Progress
1 | Enable User Detection | Enable Listener to check detection state | 5 | 0.5 | 2020-05-22 | 2020-06-01 | 100%
2 | Catch "abort" status for tts |  | 5 | 0.5 | 2020-05-22 | 2020-06-01 | 100%
3 | Catch "cancelled" status for tts |  | 5 | 0.5 | 2020-05-22 | 2020-06-01 | 100%
4 | Stop on user detection |  | 5 |  | 2020-05-22 | 2020-06-01 | -1%
5 | Display state on textArea |  | 5 |  | 2020-05-22 | 2020-06-01 | 100%
6 | Wait on arrive at location |  | 5 |  | 2020-08-07 |  | 100%
7 | Announce moving and greeting |  | 5 |  | 2020-08-07 |  | 100%
8 | Ambient noise | Play music | 5 |  | 2020-08-07 |  | 100%
9 | Make it not interrupt or repeat itself when speaking. | Implement a something that disables detection listener until the tts has finished | 8 | 4 | 2020-08-14 |  | 100%
10 | Hear custom voice commands. | Look into Temi NLP intent | 0 |  | 2020-08-14 |  | -1%
11 | Music Choices (seasonal) | op menu list, permanence will have to access device storage | 0 |  | 2020-08-14 |  | -1%
12 | Measure remaining liquid | strain gauge, pressure sensor, bt/wifi with switch, RasPi | 0 |  | 2020-08-14 |  | -1%
13 | Planning Part 2 |  |  | 3 | 2020-11-12 |  | 80%
14 | Programming: Autonomous Deployment |  |  | 8 | 2020-11-13 |  | 0%
15 | Programming: UX |  |  | 6 | 2020-11-14 |  | 0%
16 | Programming: Autonomous Interaction |  |  | 5 | 2020-11-15 |  | 0%
17 | Programming: Testing |  |  | 8 | 2020-11-16 |  | 0%
18 | Programming: Cleanup |  |  | 4 | 2020-11-17 |  | 0%
19 | Mechanical Manufacture mounting parts |  |  | 4 | 2020-11-18 |  | 0%
20 | Mechanical: Manufature mounting plates |  |  | 4 | 2020-11-19 |  | 0%
21 | Mechanical: Order fasteners |  |  | 1 | 2020-11-20 |  | 0%
22 | Administration: UserDoc |  |  | 8 | 2020-11-21 |  | 0%
23 | Administration:Training |  |  | 5 | 2020-11-22 |  | 0%
24 | Hospital: UI Changes and Polish |  |  | 6 | 2020-11-23 |  | 0%
25 | Hospital: Languages |  |  | 3 | 2020-11-24 |  | 0%
26 | Hospital: Branding Instructions |  |  | 3 | 2020-11-25 |  | 0%
27 | Extension: Manual reset |  |  | 4 | 2020-11-26 |  | 0%